# Helix 6-Week Roadmap

Generated and refreshed from repository inspection on 2026-03-18.

# Planning Basis

The current product surface is already broader than the older top-level docs imply: onboarding, Assistant, Glasses, History, Record, Settings, file management, provider configuration, native iOS speech, BLE integration, and dashboard handoff are all present in the repo.

The most current near-term work is concentrated in the recent realtime transcription and realtime conversation specs under docs/superpowers.

The older PLAN.md and todo.md still point to unresolved recording UI and waveform work, but they refer to an older ConversationTab shape that no longer matches the active RecordingScreen path.

The Assistant surface already contains dormant building blocks for richer UI and tooling, including assistant profiles, quick-ask presets, summary toggles, follow-up toggles, response tool widgets, and insight extraction helpers.

The Home screen now also has a viable loadout and setup surface for assistant tooling, so the remaining Week 3 work is about reliability and polish, not inventing a new UI path.

History sessions can already be summarized into reusable metadata, so the roadmap can now include copyable review briefs and signal counts without introducing a new persistence layer.

The next six weeks should harden and verify the current stack. This repo is already built around singleton services, platform channels, and native iOS dependencies, so a major architecture rewrite would add risk without helping the beta path.

# Constraints to Honor

Keep Flutter UI, native iOS speech/BLE code, and existing service singletons working incrementally.

Resolve audio session conflicts before adding more product scope. The recording flow already defers flutter_sound initialization to avoid clashes with live speech recognition.

Reconcile stale planning docs with the current code before execution starts, or the team risks delivering against the wrong surface.

Build a Flutter-aware verification path. The current GitHub workflow is generic Xcode only, and the repo has no integration_test/ directory.

# Milestones

## Milestone 1 - Repo Truth Locked and Transcription Stable

Target: End of Week 2

Reconcile older planning docs with the current app surface and produce one active backlog.

Stabilize transcription backend and microphone source switching across OpenAI, Apple Cloud, Apple On-Device, glasses mic, and phone mic paths.

Establish a repeatable local and CI verification baseline for analyze, test, and build.

Acceptance criteria

Old ConversationTab planning is mapped to the current RecordingScreen and Assistant flows or explicitly retired.

Permission, missing-key, auth, and fallback failures surface clearly to the user and do not silently fail.

transcriptionBackend, transcriptionModel, and preferredMicSource are validated on the intended paths.

The team has one agreed verification entry point for lint, test, and build.

## Milestone 2 - Realtime Assistant Loop Reliable

Target: End of Week 4

Harden openaiRealtime conversation mode so transcript and AI response streams stay coherent.

Improve HUD delivery, dashboard handoff, and history persistence around the realtime path.

Package session metadata into a copyable review brief in History so saved sessions include summary, action items, and verification signals.

Surface dormant assistant tooling on the Home screen: follow-up chips, summary access, response actions, insight cards, and a visible setup/loadout surface that matches the existing settings and profile model.

Finish the unresolved recording-tab stabilization work so Record, Assistant, and History behave like one product.

Acceptance criteria

Realtime transcript events and AI response events run through one stable session without duplicate downstream LLM calls.

The Assistant tab exposes response tools, insight-driven UI, and setup/loadout controls that are powered by the existing conversation engine and settings model rather than hardcoded placeholder content.

Glasses delivery, dashboard tilt, and reconnect behavior recover cleanly from native or provider failures.

Audio files, transcripts, and saved turns have a clear lifecycle and retention rule.

The highest-risk realtime and recording flows have targeted test coverage or scripted manual QA.

## Milestone 3 - Beta Ready Build and Release Gate

Target: End of Week 6

Tighten CI and release verification.

Polish onboarding, settings diagnostics, and user-facing failure states.

Run simulator, device, and glasses-hardware validation and cut a beta candidate.

Acceptance criteria

Flutter analyze, Flutter test, and at least one iOS or macOS build pass in the supported environment.

No open P0 or P1 issues remain across Assistant, Glasses, History, Record, and Settings.

Hardware validation covers glasses mic, phone mic, reconnect, offline fallback, and provider auth failure paths.

Release notes, known issues, and a go or no-go checklist are published.

# Week-by-Week Plan

| Week | Focus | Weekly goals | Deliverables |
| --- | --- | --- | --- |
| 1 | Repo truth and release scope | Reconcile current code against older docs, confirm active surfaces, map native iOS dependencies, and define the beta scope | Repo truth matrix, active backlog, verification checklist |
| 2 | Transcription stabilization | Validate backend switching, mic source fallback, permission flow, missing key handling, and auth/network recovery | Stable transcription settings flow, fallback test notes, Milestone 1 evidence |
| 3 | Realtime conversation reliability and assistant tooling | Harden openaiRealtime, verify transcript plus AI response routing, tighten status transitions, and surface summary, follow-up, insight, and setup/loadout tooling on the Assistant tab | Realtime conversation beta path, assistant response tools and setup loadout, targeted tests or QA scripts |
| 4 | Recording, history, and persistence | Align Record, Assistant, and History around one session lifecycle, resolve stale ConversationTab work, package review briefs in History, and clean up retention rules | Recording-tab stabilization, history consistency fixes, copyable review brief, Milestone 2 evidence |
| 5 | CI, UX polish, and operations | Improve onboarding and settings diagnostics, add release-facing instrumentation, and replace or extend the generic Xcode workflow with Flutter-aware checks | Flutter-aware CI plan or workflow, polished setup diagnostics, beta readiness checklist |
| 6 | Regression and beta cut | Run simulator, device, and hardware validation, burn down blockers, and prepare TestFlight release notes and go/no-go review | Beta release candidate, regression report, go or no-go summary |

# Dependencies

Even Realities glasses hardware is required for BLE mic, HUD, dashboard tilt, and handoff validation.

OpenAI API access with realtime quota is required for the primary transcription and live conversation paths.

Xcode, CocoaPods, Flutter, and a writable toolchain environment are required for end-to-end build verification.

Product decisions are needed on beta scope, especially whether openaiRealtime ships broadly or behind a controlled rollout.

QA coverage needs both simulator and on-device passes because the highest-risk flows cross Flutter, native iOS, and hardware boundaries.

# Risks

Planning drift: older docs still target ConversationTab, while the current code centers on RecordingScreen and ConversationListeningSession.

Audio stack fragility: the app already documents audio-session conflicts between flutter_sound and speech recognition, so changes in one path can break another.

Dormant feature drift: summary, follow-up, and response-action settings already exist in the repo, so leaving them disconnected from the Home screen creates UX inconsistency and raises support cost.

Hardware dependence: a large share of user value depends on glasses connectivity and native platform channels that cannot be fully covered by the current test suite.

Verification gap: CI is not yet Flutter-aware and there is no integration_test/ suite, so regressions can slip through unless week 1 and week 5 close that gap.

Documentation drift: top-level architecture docs describe future phases that are already partially implemented, which can distort planning if left uncorrected.

# Recommended Execution Order

Start with repo-truth cleanup and verification because every later week depends on knowing which flows are current and how they are validated.

Stabilize transcription before realtime conversation polish because the realtime path depends on the same native speech and mic-source plumbing.

Resolve recording and history lifecycle issues before the beta cut so support and QA have one consistent mental model for saved sessions.